# Appendix 1 - Exercise Plan

Local Emergency Management Committee Disability Inclusive Exercising Toolkit - DISCEX

Contents

Exercise Plan 1

Exercise [Name] - Exercise Plan 4

Background 4

Need 4

Overview 5

Participants 5

Exercise Aim and Objectives 5

Aim 5

Exercise Objectives & Performance Measures 5

Exercise Scope 8

Exercise Outline 8

Exercise Name 8

Exercise Type 8

Scenario 9

Proposed delivery 9

Governance and Management Structure 9

Exercise Planning Group 9

Exercise Control Group 9

Exercise Briefings 10

SMEACS Format 10

Exercise Termination 11

Public Information 11

Evaluation Plan 11

Purpose of Evaluation 11

Process of Evaluation 12

Data Collection & Observation 12

Data Analysis 12

Exercise Debriefs 12

Evaluation Report 13

Budget 13

Anticipated Expenses 14

Timeline 14

Points of Contact 14

Exercise Plan Approval 15

Attachments 15

Exercise Outputs 15

FY25/26 Emergency Management Exercise Program Key Dates 16

Exercise Briefings and Debriefings 16

EXCON Staff Responsibilities 19

EXCON Roles & Responsibilities Checklist 21

## Exercise [Name] - Exercise Plan

Refer to Sections 2 and 3 of the LEMC Disability Inclusive Exercising Toolkit for guidance in populating fields within this Exercise Plan.

### Background

LEMCs play an important role in embedding disability inclusive approaches into emergency management plans, policy and practice across prevention, preparation, response and recovery.

Local emergency plans (including consequence management guides) must consider the extra supports that people with disability need and how they will be considered and addressed in emergencies.

### Need

There is a need to [raise awareness of/explore/test/validate] local emergency management arrangements, including the capability of the Local Emergency Operations Centre (LEOC) to manage the consequences of a [emergency event], incorporating a focus on coordinating support for people with disability.

This need arises from findings and recommendations from recent reviews and inquiries into disaster events in NSW, which highlighted gaps in planning and coordination to support people with disability during emergencies. Disability inclusive emergency management arrangements require further development to ensure timely assistance, accessible communication and equitable support for people with disability.

Specific areas of focus include:

- Examining the inclusion and suitability of disability inclusive arrangements in local emergency management plans.

- Evaluating coordination of support for people with disability across all phases of the response from initial warnings through active response to the early stages of recovery.

- Examining the effectiveness of coordinated emergency response arrangements across agencies and in collaboration with disability organisations.

- Exploring the effectiveness of accessible warnings and public information and dissemination through communication channels.

- Testing decision-making processes and escalation pathways.

- Evaluating transport, shelter assets and health and welfare support for people with disability.

- Evaluating participant’s disability awareness and identifying knowledge and skills gaps among LEMC and LEOC members, as well as any training needs.

### Overview

[Tailor the overview for your exercise]

This discussion-based exercise will examine the effectiveness of disability-inclusive emergency management arrangements during a [emergency event]. A key focus will be on how the LEOC coordinates with Functional Areas, local councils, emergency services, and disability support organisations to address the additional support needs of people with disability.

The exercise will [explore/assess] the adequacy of communication and information-sharing mechanisms to ensure warnings, updates, and information are accessible to all community members, as well as the suitability of systems and processes that support accessible emergency communication.

Participants will also explore the effectiveness of transport and evacuation arrangements for people with disability, their equipment, and assistance animals, and assess the accessibility and safety of evacuation centres and other shelter options. The discussion will extend into early recovery, considering how recovery committees, disability service providers, and community organisations can work collaboratively to ensure equitable access to recovery services and supports for people with disability.

LEMCs and LEOCs are the primary target audience for this exercise, while membership between the two often overlaps, care should be taken to ensure that all relevant liaison officers expected to attend the LEOC for the chosen scenario are invited to participate.

## Participants

Participants in this exercise will include:

[List participants and the agencies they represent – exercises that include a disability focus should always include disability representative stakeholders]

## Exercise Aim and Objectives

### Aim

To assess local emergency management arrangements and strengthen the planning, and coordination of the LEMC/LEOC in preparing for and managing the consequences of a [event].  The exercise will evaluate and strengthen the capability of the LEMC/LEOC to coordinate, communicate and deliver inclusive emergency management arrangements that meet the additional support needs of people with disability.

[Insert additional or alternate aim as required]

### Exercise Objectives & Performance Measures

Select objectives and measures for your exercise

Test how effectively the LEOC coordinates with the relevant Functional Areas including Transport, Health, and Welfare Services, local councils, emergency services, and community disability support agencies in addressing the extra support needs of people with disability.

- Participants clearly identify roles and responsibilities of LEOCs, Functional Areas, local councils and disability service providers during discussion of the scenario.

- Disability coordination/liaison officers are identified for disability related requests at the EOC.

- Decision-making processes and escalation pathways are described consistently across agencies.

- Coordination challenges are recognised and potential solutions discussed collaboratively.

[Insert additional standard measures as required]

Assess the adequacy of communication channels and information sharing mechanisms to ensure warnings, updates and information are accessible to all community members.

- Disability networks are identified to support two-way communication channels between the EOC and local disability sector.

- Information-sharing processes are established with local disability networks.

- Gaps in communication channels between the EOC and disability networks are acknowledged and documented for future review.

- Participants explore how disability data and local knowledge can be used to identify and support at-risk individuals.

- Strategies to reach people with disability who live independently and may be isolated or vulnerable are identified.

- Opportunities to enhance communication and information sharing between stakeholders are identified and recorded for follow-up.

[Insert additional standard measures as required]

Assess the adequacy of existing systems and processes to deliver accessible emergency warnings, information and updates to all community members with disability.

- Participants identify the multiple channels (SMS, radio, social media, Auslan videos, Easy Read, captioned broadcasts) used to distribute accessible warnings and information.

- Accessibility gaps (e.g., missing captions, lack of interpreters, unclear signage) are identified and recorded for improvement.

- Participants demonstrate awareness of plain language principles and inclusive communication practices.

- Observations from people with disability confirm that key safety information was understandable and supported people to act on the information provided.

- Predeveloped accessible templates for emergency warnings and public information are identified.

- Lessons are incorporated into future communication plans, templates, and staff training.

[Insert additional standard measures as required]

Test the adequacy of LEOC arrangements for providing timely, secure and accessible transport options to support evacuation of people with disability, their equipment and assistance animals.

- Roles and responsibilities for transport coordination for people with disability in emergencies are clearly assigned.

- The needs of people with disability and additional support requirements, including equipment and assistance animals are incorporated into transport planning and arrangements.

- Participants describe processes and systems for identifying and prioritising evacuation of people with disability in a timely manner, consistent with emergency plans and procedures.

- Opportunities for EOC coordination with transport providers, emergency services, and disability/animal support agencies are identified.

- Resource limitations of accessible transport options are recognised and potential solutions discussed collaboratively.

[Insert additional standard measures as required]

Assess the suitability and adequacy of evacuation centres and other shelter options in providing physically safe and accessible venues for people with disability.

- Accessibility audits/checklists are completed for all identified evacuation centres on a regular basis.

- Alternative accessible places of shelter or emergency accommodation are identified.

- Plans for mobilising disability supports such as accessible transport, communication aids and personal assistance are identified in accordance with relevant plans.

- Evacuation Centre staff and volunteers have undertaken disability awareness training.

- Post-exercise debrief identifies accessibility barriers.

[Insert additional standard measures as required]

Explore how recovery committees, disability service providers and community organisations work together to ensure equitable access to recovery services and supports for people with disability during the early recovery phase.

- Recovery committees demonstrate effective coordination with disability service providers and community representatives.

- The recovery centre provides safe, accessible, and inclusive services that meet the needs of people with disability.

- People with disability and their representative organisations are actively included in recovery planning through subcommittees, reference groups, community resilience networks.

- Opportunities for improving partnerships, processes and accessibility are recorded for post exercise debrief.

[Insert additional standard measures as required]

## Exercise Scope

[Select and insert additional scope items as appropriate for your exercise]

In Scope:

- EOC control and coordination structures

- Coordination considerations from warning through impact to early recovery

- Roles, tasks and expectations of emergency services, functional areas and disability service providers

- Evacuation centre accessibility

- Accessible transport options

- Accessible communications and messaging

- Identifying resources and capabilities of disability support organisations and people with disability

- Building connections and working in partnership with local disability representatives and advocacy agencies.

Out-of-scope:

- Physical activation and set up of an EOC

- Physical activation and set up of an evacuation centre

- Strategic issues decided at state level.

## Exercise Outline

### Exercise Name

[Insert]

### Exercise Type

This exercise will be conducted as a facilitated hypothetical discussion, where participants will respond to evolving emergency scenarios presented with minimal prior notice. Guided by a skilled facilitator, participants will engage in group discussions to address a series of trigger questions, allowing for an assessment of their outputs against the defined exercise objectives.

The facilitator will introduce thought-provoking questions and unexpected developments to steer the discussion, fostering a shared understanding of emergency strategies and procedures. This format is well-suited to a group discussion, ideal for an LEMC/LEOC sized team. Effective preparation and an experienced facilitator are essential to ensure meaningful outcomes.

### Scenario

This exercise will focus on [Insert detail on chosen scenario].

### Proposed delivery

The exercise is proposed for delivery on [date] at [venue].

The exercise will be conducted by a suitably experienced facilitator appointed by the exercise planning group.

## Governance and Management Structure

### Exercise Planning Group

An exercise planning group will be established to lead the planning and preparation of the exercise.  The planning group will be chaired by [name] from [agency] and include the following members:

- [List planning group representatives]

### Exercise Control Group

An Exercise Control (EXCON) Group will be established for the purpose of running and facilitating the exercise. Below is a list of members on the EXCON Group:

[Refer to EXCON Staff Responsibilities for a list of all roles and associated functions]

| Role | Assignee |
| --- | --- |
| Exercise Director | [INSERT NAME] |
| Exercise Planning Coordinator | [INSERT NAME] |
| Exercise Controller | [INSERT NAME] |
| Exercise Facilitator | [INSERT NAME] |
| Logistics Coordinator | [INSERT NAME] |
| Exercise Evaluation Coordinator | [INSERT NAME] |
| Disability Inclusion Advisor | [INSERT NAME] |
| Disability Inclusion Evaluator | [INSERT NAME] |
| Exercise Evaluators | [INSERT NAME/S] |

### Exercise Briefings

Before beginning the exercise, the following groups should be briefed:

Participants

Evaluators

Additional briefings may also be necessary, depending on the exercise setup e.g. Observer Briefing.

Briefings should be delivered by someone with in-depth knowledge of the exercise and its intended outcomes, such as the Exercise Controller or a designated representative.

Briefings can take place immediately before the exercise or during the preparation phase, provided there isn’t an extended gap that could cause attendees to forget critical information.

All briefings should follow the SMEACS format outlined below and, at a minimum, cover:

Exercise aim and objectives

Scenario overview (without revealing specific surprises or injects, unless essential for the group)

Overview of disability inclusive elements in the exercise

Suggested pre reading or online training (the Emergency Sector Disability Awareness (ESDA) is recommended)

Relevant roles and responsibilities for the group being briefed and

Copies of any relevant documents.

### SMEACS Format

Situation: A summary of the current circumstances, including relevant background information and context.

Mission: A clear and concise statement of the task or objective to be achieved.

Execution: The plan detailing how the mission will be accomplished, outlining strategies, tactics, and specific tasks.

Administration and Logistics: Information on support elements such as resources, supplies, personnel, and logistical considerations necessary for the operation.

Command and Communications: Details about the command structure, reporting lines, and communication protocols to ensure coordination among all parties involved.

Safety: Identification of potential hazards and safety measures to protect personnel and assets during the operation.

## Exercise Termination

The exercise will formally conclude once the facilitator has completed the final trigger question of the exercise and the post-exercise debrief has been conducted. Refer to Appendices 5 to 5D for guidance on evaluation processes including debriefs.

Determine maximum duration for your exercise to run, up to four hours is a suggested timeframe. If the exercise is not completed within this timeframe, the Exercise Director may determine whether to conclude the activity at that point or extend the session to complete the remaining content.

## Public Information

Responsibility for any media engagement during the exercise rests with the LEMC. Where real or simulated media involvement is anticipated, it is recommended that the LEMC engage an internal media representative or communications specialist to participate in both the planning and conduct phases, to ensure effective and coordinated media management.

In cases where combat and support agencies anticipate media engagement as part of their exercise roles, agency representatives should coordinate with their respective media departments and consider involving agency media personnel in the exercise.

Regardless of anticipated media activity, all participating organisations should consider advising their internal media departments about the exercise to facilitate smooth communication and alignment.

## Evaluation Plan

### Purpose of Evaluation

The primary purpose of exercise evaluation is to assess both the effectiveness of the exercise and how well it met its stated aims and objectives.

A rigorous evaluation process enables planners and operational managers to systematically enhance future exercises, as well as related procedures, processes, and operational initiatives. Through observation, data collection, analysis, and reporting, evaluation transforms insights gained from the exercise into practical improvements for future operations.

Exercise evaluation involves a series of post-exercise activities focused on:

Gathering feedback and assessing the conduct of the exercise

Collecting insights on participant experiences

Evaluating the achievement of exercise objectives

Transferring lessons learned into lesson management systems

The exercise analysis should consider:

Did the exercise achieve its aims and objectives?

Do current plans, policies and procedures support effective engagement with disability service providers?

What worked well? (considering operational activities and exercise logistics)

What could be done differently?

What capabilities and strengths were identified?

How might identified resource issues be resolved?

What areas require further planning?

What would improve future exercises?

### Process of Evaluation

To facilitate a smooth and effective evaluation, an Exercise Evaluation Coordinator should be appointed prior to the exercise. The Coordinator’s primary role is to manage the overall evaluation process and lead the team of evaluators.

One or more evaluators should be appointed to assist with data collection and observation throughout the exercise. The number of evaluators required will depend on the exercise cohort size and the volume of data to be gathered. For smaller groups, the Exercise Coordinator may take on both evaluator and coordinator roles.

### Data Collection & Observation

Data and observations will be gathered during and after the exercise using the following tools:

Participant Feedback Sheet (Appendix 5A)

After-Action Review Debrief Form (Appendix 5C)

Observer’s Checklist (Appendix 5D)

The EXCON may implement additional data collection methods as appropriate.

### Data Analysis

Upon completing the exercise, evaluators will return all completed data collection tools to the Exercise Evaluation Coordinator. The Coordinator will then compile and analyse the collected data and observations, documenting insights and lessons in the analysis tables within the Evaluation Plan.

### Exercise Debriefs

An essential component of a successful exercise is the ability to debrief the activities of the conduct phase. A series of debriefs will be required at the conclusion of an exercise. Depending on the scale of the exercise these may include:

informal ‘hot’ debrief (immediately post-exercise) for:

Participants

EXCON

formal debriefs for:

organisation-specific debrief

a formal multi-organisation debriefs involving all participants and EXCON team members

exercise management debrief.

In all cases the debrief must be planned and communicated to all those who need to be involved. During the debrief process, detailed information is collected at a lower level, with that information contributing to higher-level and subsequent debriefs.

### Evaluation Report

Exercise Evaluation Reports should be produced to effect change and improvements. Reports do not have to be extensive to achieve that. Evaluation Reports should clearly identify areas or issues to be improved. They should include enough context for each issue or provide links to that context. If opportunities for improvement or recommendations are identified, they can be included.

For exercises that incorporate a disability focus, the evaluation report should clearly identify the key findings and lessons to inform disability inclusive emergency management planning. Refer to Appendix 5 for an Evaluation Report template including disability considerations.

For a small exercise, there may be one evaluator who produces a one-page report. For a large exercise there may be several individual evaluator reports that need to be analysed and summarised into the final evaluation report.

The Exercise Evaluation Coordinator may be asked to draft the evaluation report on behalf of the Exercise Director. The Exercise Director is responsible for finalising the evaluation report and then sending it to those responsible for resolving the opportunities for improvement or recommendations that have been identified.

For exercises funded via the Premier’s Department Emergency Management Exercise Program, the final Evaluation Reports must be submitted to the Premier’s Department and will contribute to the annual State Lessons Analysis process.

Any collateral generated from the exercise (e.g., photos, videos, case studies) should also be provided to the Premier’s Department to support a shared resource cache for agency reference and use.

## Budget

Exercises are generally funded through existing business as usual arrangements unless alternative fundings sources are identified. The LEMC, its member agencies and partners are responsible for meeting exercise related costs, as appropriate to their roles and participation.

Costs are expected to be shared across participating agencies and partners, with contributions managed in line with local agreements and existing interagency support arrangements.

In FY25/26, the Emergency Management Exercise Program administered by the Premier’s Department makes funding available to LEMCs for eligible ancillary costs associated with disability inclusive emergency management exercises. Further information is available within the Program Guidelines available here.

### Anticipated Expenses

Anticipated expenses associated with the conduct of the exercise may include, but not be limited to:

| Expense | Responsible Entity |
| --- | --- |
| Venue Hire | LEMC |
| Catering | LEMC |
| Staffing | Individual Agencies / Organisations |
| Travel & Accommodation | Individual Agencies / Organisations |
| Exercise Materials & Documentation | LEMC |
| External Exercise Facilitator (if required) | LEMC |

## Timeline

[Outline the proposed timeline for the planning, conduct and evaluation of the exercise]

| Category | Responsible | Due by |
| --- | --- | --- |
| Concept | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |
| Planning | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |
| Conduct | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |
| Evaluation and reporting | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |

## Points of Contact

[List key contact persons involved in the overall planning and coordination of this exercise.

Include person’s name, work area, phone and email]

| Name | Position | Contact Details |
| --- | --- | --- |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |

## Exercise Plan Approval

| Approved / Not Approved | Approved / Not Approved |
| --- | --- |
| ______________________________ | ________________________________ |
| Name Title | Name Title |
| Date | Date |

## Attachments

### Exercise Outputs

The outputs from the exercise conduct and evaluation phases may include:

| Conduct Phase | Evaluation Phase |
| --- | --- |
| Participant learning Organisational learning REMC / LEMC learning Debriefing Post exercise evaluation report Observations capture Lessons identified Procedure / tool evaluation | Evaluation report Stakeholder feedback Inputs into lessons management processes Actions arising from evaluation reports are passed to responsible individual / organisations |

### FY25/26 Emergency Management Exercise Program Key Dates

For LEMCs that receive funding from the Premier’s Department to support delivery of this exercise, the following key dates should be noted:

| Date | Task |
| --- | --- |
| 1 August 2025 | Expressions of interest for funding open |
| 1 June 2026 | Expressions of interest close |
| 12 June 2026 | Reimbursement invoices due to Premier’s Department |
| 1 August 2025 – 30 June 2026 | Exercises held |
| 31 July 2026 | Exercise evaluation reports and collateral due to Premier’s Department |

### Exercise Briefings and Debriefings

#### Briefings

Use the table below to document each planned briefing, specifying the type of briefing, target audience, presenter, and scheduled timing. This will help ensure all briefings are organised and delivered as planned.

| Briefing Type | Target Audience | Presenter | Scheduled Timing |
| --- | --- | --- | --- |
| eg. Pre-Exercise Briefing | All participants | John Smith | Immediately before exercise |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |

Use the table below to document content from the briefings, in SMEACS format.

| Section | Content |
| --- | --- |
| Situation | Provide a brief overview of the current situation or context that necessitates action or response. eg; "A fire has broken out in the facility’s kitchen area, requiring an evacuation and activation of emergency response procedures." |
| Mission | Clearly state the objective or purpose of the operation or response. eg: "The mission is to ensure all personnel evacuate safely and assess the effectiveness of emergency response procedures." |
| Execution | Outline specific tasks, roles, and the sequence of actions expected to achieve the mission. eg: "Personnel will follow assigned evacuation routes, report to assembly points, and respond to communications from the control team." |
| Administration & Logistics | Detail logistical arrangements, including available resources, equipment, and other support requirements. eg: "The designated assembly area will be in the parking lot, with first aid kits and radios distributed to team leaders." |
| Command & Control | Define who is in charge, clarify the command structure, and specify reporting lines and communication protocols. eg: "The Incident Commander is in charge; all team leaders report to them, and communication will occur over designated radio channels." |
| Safety | Highlight safety precautions, potential risks, and any procedures to ensure participant safety. eg: "Use marked evacuation routes only. The term ‘No Duff’ will be used to indicate a real emergency. First aid is available on-site if needed." |

#### Debriefs

Use the table below to document each planned debrief, specifying the type of debrief, target audience, presenter, and scheduled timing. This will help ensure all debriefs are organised and delivered as planned.

| Debrief Type | Target Audience | Presenter | Scheduled Timing |
| --- | --- | --- | --- |
| eg. Hot AAR Debrief | Exercise participants | John Smith | Immediately after exercise termination |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |

### EXCON Staff Responsibilities

#### Exercise Director

Appoints Exercise Control Staff and Evaluation Coordinator

Facilitates exercise planning including time, date, style, scenario and scope

Facilitates development of all documents including Concept Plan, Master Schedule of Events, Risk Management Plan, Participant Instructions, Control Staff Instructions and Evaluation Plan

Ensures the exercise stays within scope

Coordinates the funding, resources, catering, and agencies

Authorises alterations to the planned program

Coordinates and prepares the Final Evaluation Report

Authorised person to start, suspend or conclude the exercise

#### Exercise Controller

Manages Master Schedule of Events for the exercise event site

Manages all Exercise activities relative to the exercise event site

Ensures adequate opportunities exist to achieve exercise and agency objectives

Manages safety and risk in accordance with approved plans

Simulates activities not performed by participants

Assists and contributes to debriefs

Contributes to the Exercise Evaluation Report

#### Exercise Planning Coordinator

Assists in the development of exercise objectives, scope, and scenarios

Supports the creation of key documents (Concept Plan, Master Schedule, Participant Instructions)

Identifies and assesses potential risks

Ensures all planning aligns with the exercise goals and maintains realistic scenarios

#### Disability Inclusion Advisor

- Provides expert guidance on disability inclusive emergency management in the planning, conduct and evaluation of the exercise.

- Assists in the selection and development of exercise objectives, special ideas and injects with a disability focus.

- Assists the facilitators and evaluators to recognise inclusion related issues and to identify opportunities for disability inclusive planning and actions.

#### Exercise Facilitator

Leads the exercise discussion and guides participants through the scenario

Poses questions and prompts to encourage active engagement and critical thinking

Facilitates the delivery of the desktop-based functional components of the exercise.

Maintains the flow of the exercise, ensuring discussions stay within scope and timeframe

Provides clarifications on exercise scenarios and objectives as needed

Observes participant responses and interactions for evaluation purposes

Coordinates with the Exercise Controller on any required adjustments during the session

#### Exercise Evaluation Coordinator

Appoint and coordinate exercise evaluators

Provide briefings, guidance, and support to evaluators

Facilitate after-action reviews, including hot and formal debriefs

Collate feedback and evaluation reports from both participants and evaluators

Prepare the exercise evaluation report on behalf of the Exercise Director

#### Exercise Evaluators

Appointed by Exercise Evaluation Coordinator

Watches and listens to the exercise

Be fully briefed and know exercise objectives and key performance measures

Measures and evaluates the conduct and outcomes of exercise activities and records outcomes against specified performance measures

Makes notes to assist the debrief and Evaluation Report

Assists or leads the hot debrief for their agency after the exercise, as required

Assists and contributes to the formal debrief

#### Disability Inclusion Evaluator

- Assesses how effectively disability inclusion is considered and implemented throughout the exercise

- Observes discussions, decisions, and actions to identify strengths, gaps, and opportunities for improvement in meeting the needs of people with disability

- Provides feedback on the accessibility of communication, coordination, and service delivery arrangements

- Contributes to the overall evaluation report with findings and recommendations that enhance disability inclusive emergency management practices

#### Logistics Coordinator

Liaises with venue owners or operators

Coordinates catering and welfare requirements

Arranges transport of participants and equipment

Commissions preparation of tools, resources and documents required for the exercise

Procures additional equipment, consumables, and resources, as required

Sets up registration or administration areas for exercise control.

[Insert additional responsibilities as required]

### EXCON Roles & Responsibilities Checklist

| Role | Checklist |
| --- | --- |
| Exercise Director | Before Exercise - Approve exercise aim, objectives, and key documentation. - Confirm and authorise budget and resources with stakeholders. - Appoint and authorise all EXCON roles, including the Exercise Facilitator. - Finalise and communicate the exercise date, time, and venue to all stakeholders. - Confirm communication protocols with key stakeholders and external agencies to ensure alignment. - Review the scenario with the Exercise Planning Coordinator. - Schedule a high-level briefing for senior leaders or stakeholders on objectives, scenario, and expected outcomes. - Authorise any required changes to the exercise program or plan. During Exercise - Authorise commencement, termination, or suspension of the exercise as needed. - Supervise the conduct phase to ensure alignment with objectives. - Monitor participant engagement and authorise adjustments as necessary. - Coordinate real-time adjustments with EXCON and facilitators as needed. After Exercise - Confirm that debriefs and evaluation processes are completed. - Review, approve, and submit the final evaluation report to the Premier’s Department, ensuring all findings and recommendations are included. - Verify that all funding reimbursement requests and required documentation are submitted to the relevant authorities. [Insert additional items as required] |
| Exercise Controller | Before Exercise - Review and understand the Exercise Scenario and timing of activities. - Confirm site-specific activities align with objectives and ensure resources are prepared. - Familiarise yourself with the safety and risk management plan. - Plan and prepare simulations for non-participant activities as required. - Ensure all relevant parties are briefed, delivering pre-exercise briefings if needed. During Exercise - Oversee and manage the timing and execution of the exercise, adjusting as necessary. - Monitor exercise activities to ensure alignment with objectives, adjusting flow as needed. - Actively manage site safety, responding to incidents according to the risk plan. - Simulate activities not performed by participants as required. - Facilitate participant engagement to meet exercise and agency objectives. After Exercise - Participate in debrief sessions, providing feedback on exercise flow and participant engagement. - Contribute observations and insights to the Exercise Evaluation Report. - Complete and submit safety and incident reports for any incidents during the exercise. - Assist in facilitating and leading debriefs as needed. [Insert additional items as required] |
| Exercise Planning Coordinator | Before Exercise - Develop and finalise the detailed exercise plan. - Confirm roles, responsibilities, and appointments within the EXCON structure. - Finalise all required documents (evaluation plans, injects, scenarios). - Complete the scenario and injects, ensuring all elements are fully developed and aligned with objectives. - Distribute essential documents (e.g. exercise plans, participant handbooks, role assignments) to all participants and controllers in advance. - Coordinate pre-exercise briefings and distribute exercise materials. - Establish and confirm a clear communication plan among participants, EXCON, and evaluators. - Conduct a risk assessment and prepare necessary documentation. During Exercise - Coordinate with the Exercise Controller on inject timings and scenario adjustments as needed. After Exercise - Participate in debrief and evaluation processes. [Insert additional items as required] |
| Disability Inclusion Advisor | Before Exercise - Work with the Exercise Planning Coordinator to develop and incorporate disability inclusion considerations into the detailed exercise plan. - Confirm roles, responsibilities, and appointments within the EXCON structure, including the role of the Disability Inclusion Evaluator. - Ensure that all required documents evaluation plans, injects and scenarios incorporate disability inclusive elements. - Work with the Exercise Planning Coordinator to incorporate disability inclusive special ideas and injects into the scenario, ensuring all elements are fully developed and aligned with objectives. During Exercise - Coordinate with the Exercise Controller and Exercise Planning Coordinator on disability inclusive special ideas and inject timings adjustments as needed. - Provide advice and guidance to Exercise Controller and Exercise Planning Coordinator on disability inclusion considerations through all phases of the exercise as required. - Assist the Disability Inclusive Evaluator as required. After Exercise - Participate in debrief and evaluation process, sharing insights and feedback on observations to identify strengths, gaps and opportunities to strengthen disability inclusive actions and service delivery. [Insert additional items as required] |
| Exercise Facilitator | Before Exercise - Review the scenario, objectives, and prompts to guide participant discussions. - Review the exercise presentation and suggest any necessary changes or updates. During Exercise - Lead discussions and guide participants through each scenario phase. - Pose questions and prompts to encourage engagement and critical thinking. - Facilitate the delivery of the desktop-based functional components of the exercise. - Keep discussions on track, within scope, and aligned with the exercise timeframe. - Provide clarifications on scenarios and objectives as needed. - Coordinate with the Exercise Controller on any necessary adjustments. After Exercise - Contribute observations and insights to debrief and evaluation processes. [Insert additional items as required] |
| Exercise Evaluation Coordinator | Before Exercise - Assign evaluators to specific exercise components, ensuring full coverage. - Brief and train evaluators on observation techniques and assessment criteria. - Distribute evaluation tools, including observation templates and data collection methods. - Conduct a pre-exercise calibration meeting to review objectives, standards, and scoring criteria. - Prepare feedback mechanisms (e.g. feedback sheets, debrief sessions) for gathering insights. - Identify key observation points at the venue and station evaluators strategically. During Exercise - Support and coordinate evaluators, providing resources and assistance as needed. - Oversee observation collection to ensure validity and consistency with evaluation standards. After Exercise - Ensure after-action reviews (AARs) and debriefs are conducted, leading them as required. - Collate and analyse evaluator reports to identify key findings and improvement areas. - Draft the final exercise evaluation report, consolidating observations, feedback, and recommendations. [Insert additional items as required] |
| Exercise Evaluators | Before Exercise - Review exercise objectives, evaluation criteria, and assigned focus areas. - Familiarise yourself with observation tools and data collection methods. During Exercise - Observe participant actions and interactions according to assigned objectives. - Record observations accurately, focusing on outcomes relevant to exercise performance measures. - Coordinate with the Evaluation Coordinator for any needed clarification or guidance. After Exercise - Conduct debriefs as required. - Submit completed observation notes and any supporting documentation. - Participate in debrief sessions, sharing insights and feedback on observations. [Insert additional items as required] |
| Disability Inclusion Evaluator | Before Exercise - Review exercise objectives and evaluation criteria to ensure that disability inclusion considerations are incorporated. - Familiarise yourself with observation tools and data collection methods. During Exercise - Observe participant actions and interactions according to assigned objectives and identify strengths, gaps and opportunities to strengthen disability inclusive actions and service delivery. - Record observations accurately, with a particular focus on outcomes relevant to disability inclusion exercise performance measures. - Coordinate with the Evaluation Coordinator for any needed clarification or guidance. - Provide clarification and guidance for the Evaluation Coordinator in relation to disability inclusion. After Exercise - Submit completed observation notes and any supporting documentation. - Participate in debrief sessions, sharing insights and feedback on observations to identify strengths, gaps and opportunities to strengthen disability inclusive actions and service delivery. - Contribute to the evaluation report with findings and recommendations that enhance disability inclusive emergency management practice. [Insert additional items as required] |
| Logistics Coordinator | Before Exercise - Book the venue, ensuring it meets all setup requirements. - Arrange catering based on participant needs and confirm service details. - Send invites and agendas to all participants with event details and expectations. - Confirm all technical requirements (audio-visual aids, communication devices). - Prepare props, special equipment and documents needed for the exercise. - Visit the venue to confirm setup, ensuring equipment (e.g. projectors, seating, staging areas) is in place. - Arrange clear signage to direct participants, observers, and evaluators to appropriate areas. - Arrange inventory supplies, such as name badges, safety equipment, notepads, and pens. - Confirm transportation and parking arrangements, providing relevant information to participants. During Exercise - Open and prepare the venue, ensuring all areas are ready for use. - Confirm catering has arrived, is laid out, and is maintained throughout the event. - Address any logistical needs as they arise to support the smooth flow of activities. After Exercise - Participate in debrief sessions, providing insights on logistics and venue setup. - Contribute feedback and observations to the evaluation report. [Insert additional items as required] |