Appendix 1A

# Exercise project plan

This template is designed as a project management checklist to guide the planning team, based on a discussion exercise.

Suggested wording is in black, which you may choose to use or amend. Delete or update guidance text in red once complete.

# [EXERCISE NAME]

| Action | By | Date | Comments |
| --- | --- | --- | --- |
| Initial planning meeting |  | -8 weeks |  |
| Exercise Plan sent for approval |  | -7 weeks | Appendix 1A Usually approved by the LEMC – time this around their routine meetings |
| Exercise Plan approved |  | -6 weeks | Appendix 1A |
| Confirm planning group membership and schedule scenario development meetings |  | -6 weeks | Plan for two or three meetings of up to two hour’s duration. |
| Identify stakeholders and initiate engagement |  | -6 weeks |  |
| Issue participant invitations |  | -6 weeks | Appendix 4 |
| Finalise room/venue bookings |  | -6 weeks |  |
| Planning group meetings to develop scenario |  | 6-4 weeks |  |
| General idea, special ideas and injects finalised |  | -4 weeks | Appendix 2 |
| Exercise logistic requirements identified: Staffing Equipment (e.g., audio-visual, whiteboards) Catering Parking Signage |  | -4 weeks |  |
| Draft Facilitator Guide issued for comment |  | -4 weeks | Appendix 1B |
| Facilitator Guide approved |  | -3 weeks |  |
| Exercise support materials finalised |  | -2 weeks | Appendix 4 and 5 |
| Exercise logistics confirmed |  | -2 weeks |  |
| Exercise run-through |  | -1 week | A rehearsal may be useful |
| Conduct exercise |  | Day zero |  |
| Collate and analyse feedback |  | +2 days | Appendices 5A - 5D |
| Draft exercise report – internal review |  | +1 week | Appendix 5 |
| Draft exercise report submitted |  | +2 weeks | Appendix 5 |