# Exercise Plan

Major Evacuation Centre (MEC) Exercise - Bushfire

Contents

Exercise Plan 1

Exercise [Name] - Exercise Plan 4

Background 4

Need 4

Overview 4

Participants 5

Exercise Aim and Objectives 5

Aim 5

Exercise Objectives & Performance Measures 5

Exercise Scope 6

Exercise Outline 7

Exercise Name 7

Exercise Type 7

Scenario 8

Proposed delivery 8

Governance and Management Structure 8

Exercise Planning Group 8

Exercise Participants 8

Exercise Control 9

Exercise Briefings 9

SMEAC Format 10

Exercise Termination 10

Public information 10

Evaluation Plan 10

Purpose of Evaluation 10

Process of Evaluation 11

Data Collection & Observation 11

Data Analysis 11

Exercise Debriefs 11

Exercise Report 12

Budget 12

Anticipated Expenses 12

Timeline 13

Points of Contact 13

Approval 14

Attachments 15

Exercise Outputs 15

Exercise Program 15

EXCON Staff Responsibilities 16

Exercise Briefings and Debriefings 17

Roles & Responsibilities Checklist 20

## Exercise [Name] - Exercise Plan

### Background

The NSW Premier’s Department has developed the Major Evacuation Centre (MEC) Guidelines to enhance the state’s ability to manage large-scale evacuations and support displaced communities during significant emergencies. The Guidelines clarify roles, responsibilities, and escalation pathways across local, regional, and state levels when circumstances require the activation of a Major Evacuation Centre.

To support the release, an exercise is required to test key elements of the Guidelines. This includes validating the proposed decision-making tools, activation processes, and governance arrangements—particularly the appointment and function of the MEC Controller and Incident Management Team (IMT) roles.

The exercise will include a blend of desktop and functional elements but will not involve the full establishment of a MEC. Instead, it will focus on simulating realistic decision points and coordination challenges across all levels of emergency management.

### Need

There is a need to test and validate the effectiveness and practical applicability of the MEC Guidelines at the Regional Emergency Management Committee (REMC) level following their release.

This need arises from the increasing likelihood of large-scale displacement events in New South Wales, and the complexity involved in establishing and managing MECs across multiple levels of emergency management.

Specific areas of focus include:

Testing the use of MEC decision-making tools in realistic simulated scenario conditions.

Assessing how MEC Controller and IMT roles are understood, appointed, and operationalised.

Enhancing confidence in MEC governance structures and processes during MEC establishment scenarios.

Exploring the effectiveness of communication and coordination mechanisms across local, regional, state, and multi-agency levels.

### Overview

This exercise will provide insights into the challenges associated with activating and managing a MEC in a complex emergency setting. It will examine decision-making, governance, and the application of the MEC Guidelines in a scenario involving escalating emergency conditions.

The primary target audience for this exercise is REMCs and their members. The exercise may also be relevant to Local Emergency Management Committees (LEMC) involved in the establishment and management of a MEC.

## Participants

Participants in this exercise will include members of the REMC and representatives from participating organisations as defined in the area’s Regional Emergency Management Plan (REMP). Participants may include, but are not limited to:

Regional Emergency Operations Controller (REOCON) and Local Emergency Operations Controller (LEOCON)

Regional Emergency Management Officer (REMO) and Local Emergency Management Officer (LEMO)

REMC Combat and Supporting Agency Representatives, as relevant to the area, including:

NSW Police Force

NSW Ambulance

NSW Rural Fire Service

Fire & Rescue NSW

NSW State Emergency Service

Marine Rescue NSW

VRA Rescue

Surf Life Saving Australia

Functional Area Coordinators and Representatives

Other Stakeholders as deemed appropriate by the REMC

## Exercise Aim and Objectives

### Aim

Validate the MEC Guidelines by testing their application during a simulated major evacuation event, with a focus on decision-making, escalation pathways, and governance arrangements, including the appointment and functioning of the MEC Controller and Incident Management Team (IMT).

[Insert additional or alternate aim as required]

### Exercise Objectives & Performance Measures

Test the application and effectiveness of the MEC decision-making tools outlined in the MEC guidelines.

Participants followed logical and appropriate steps to escalate and activate a Major Evacuation Centre (MEC) in accordance with the MEC Guidelines.

Participants considered realistic and relevant factors prior to initiating a request for MEC activation.

Participants correctly identified and selected the appropriate tools required to request MEC activation, consistent with the MEC Guidelines.

The MEC Activation Checklist was used as intended to support the decision-making process for activating a MEC.

The MEC Activation Checklist was considered useful and effective by participants in guiding the activation decision.

The MEC Risk Assessment Template was used to inform the request to the SEOCON for MEC activation.

The information captured in the MEC Risk Assessment Template was appropriate, sufficient, and relevant to evacuation-related risks.

Exercise observers confirmed that decision-making documentation (e.g. checklists, risk assessments) was completed in a timely and accurate manner.

[Insert additional standard measures as required]

Assess the appointment process and functional operation of the MEC Controller and Incident Management Team (IMT) roles.

- Participants identified realistic and appropriate considerations for appointing an MEC Controller from within the REMC.

- A suitably qualified individual was appointed to the role of MEC Controller during the exercise.

- Any gaps in qualifications or capability relating to the appointment of the MEC Controller were identified and documented for REMC follow-up.

- Under the direction of the appointed MEC Controller, a functional MEC IMT structure was developed in alignment with the MEC Guidelines.

- The REMC was able to staff the initial operational shift of the MEC IMT using personnel and resources available within or accessible to the region.

- Any gaps in qualifications or capability within the appointed MEC IMT were identified and documented for REMC follow-up.

- Any missing, redundant, or unclear MEC IMT roles were identified and recorded for further review and escalation to the relevant authority.

[Insert additional standard measures as required]

Validate the suitability of the governance arrangements in the MEC Guidelines, including coordination across local, regional, and state levels.

- Participants identified functional, practical, and realistic mechanisms for establishing and maintaining communication and liaison with key stakeholders, including combat agencies, local/regional/state EOCs, and community representatives.

- Any gaps in capability, systems, or procedures related to maintaining effective communication and liaison were identified and documented for REMC follow-up.

[Insert additional standard measures as required]

## Exercise Scope

This exercise involves members of the REMC, as defined in the relevant REMP. It is structured as a six-hour, discussion-based desktop exercise with integrated functional elements designed to test and validate the decision-making and governance tools outlined in the MEC Guidelines. The scenario will centre around an escalating bushfire emergency within the region.

The exercise is intended for application at the regional level and reflects the scope and responsibilities of REMCs in relation to MEC activation. It has been deliberately designed to be non-specific to any single geographic area, ensuring it can be delivered consistently across all regions of New South Wales. The exercise will not include the actual or simulated physical activation of a MEC, nor will it address the operational management of an established MEC. Instead, it will focus on the processes related to MEC activation, governance, and strategic-level decision-making.

In Scope:

REMC level decision-making and coordination activities.

Use of MEC decision-making tools, including the Activation Checklist and Risk Assessment Template.

Appointment of the MEC Controller and MEC Incident Management Team (IMT).

Interagency communication and coordination during MEC activation planning.

Documentation and observation of decisions made for exercise evaluation purposes.

Out of Scope:

Physical activation or setup of a Major Evacuation Centre.

Operational management or service delivery within an established MEC.

Involvement of the general public or real-time field deployments.

Testing of site-specific logistics or facility readiness.

Agency-specific internal procedures not related to REMC-level coordination or MEC governance.

## Exercise Outline

### Exercise Name

[To be determined by the relevant LEMC/REMC]

### Exercise Type

This exercise is a facilitator-led, discussion-based desktop activity incorporating selected functional elements. It is designed to simulate a regional level MEC activation scenario within the context of an unfolding emergency, prompting participants to work through decision-making and practical processes. The exercise will be delivered in five phases, bookended by an opening briefing and short presentation, and concluding with a debrief session. Scenario injects will be introduced progressively by the facilitator to advance the storyline and prompt participant activity.

While primarily structured as a discussion exercise, functional elements, including the use of MEC decision-making tools and templates, will be integrated at key points to test their practical application. The exercise provides a controlled environment to validate MEC decision-making processes, strengthen understanding and implementation of governance roles and responsibilities, and explore communication and coordination mechanisms, all without requiring physical deployment.

### Scenario

The exercise scenario is set in mid-summer in New South Wales, during a period of prolonged drought, above-average temperatures, and escalating bushfire activity. Multiple fires have been burning for several weeks, with intermittent threats to rural communities and increasing strain on local resources. Several short-term evacuation centres have already been activated in nearby towns, with a growing number of displaced residents requiring multi-night support and temporary accommodation.

The situation intensifies following a Bureau of Meteorology forecast of consecutive days of catastrophic fire danger. In response, the NSW Rural Fire Service delivers a regional briefing to emergency management committees, prompting discussions at the REMC level around management of large numbers of displaced persons .

The scenario provides a realistic context for participants to explore decision-making processes, governance structures, and coordination challenges associated with standing up a MEC under emergency conditions.

### Proposed delivery

The exercise is proposed for delivery on [DATE] at [VENUE].

The exercise will be conducted by a suitably experienced facilitator appointed by the exercise planning group.

The attached facilitators guide, and resources are to be used to conduct the exercise.

## Governance and Management Structure

### Exercise Planning Group

An exercise planning group will be established to lead the planning and preparation of the exercise. This group should include:

Representatives from the REMC

NSW Police Force (REMO/REOCON)

Experienced exercise planning and facilitation specialist/s

Other key stakeholders as required

The planning group will be chaired by [INSERT NAME] from [INSERT AGENCY NAME].

### Exercise Participants

Proposed agencies/participants:

Members of the REMC

NSW Police, including Regional Emergency Operations Controller (REOCON) and Regional Emergency Management Officers (REMO)

Representative of LEMCs, including but not limited to LEOCON’s, LEMC members and representatives and Local Emergency Management Officers (LEMO)

State Government Combat and Support Agencies

Functional Area Coordinators and/or Functional Area Representatives

Agencies who will be participating in the exercise include:

[INSERT NAMES OF PARTICIPATING AGENCIES]

### Exercise Control

An Exercise Control (EXCON) Group will be established for the purpose of running and facilitating the exercise.

EXCON Roles are listed below. See appendix below for responsibilities of each of the below roles.

| Role | Assignee |
| --- | --- |
| Exercise Director | [INSERT NAME] |
| Exercise Planning Coordinator | [INSERT NAME] |
| Exercise Controller | [INSERT NAME] |
| Exercise Facilitator | [INSERT NAME] |
| Logistics Coordinator | [INSERT NAME] |
| Exercise Evaluation Coordinator | [INSERT NAME] |
| Exercise Evaluators | [INSERT NAME/S] |

### Exercise Briefings

Before beginning the exercise, the following groups should be briefed:

Participants

Evaluators

Additional briefings may also be necessary, depending on the exercise setup:

Observer Briefing

Briefings should be delivered by someone with in-depth knowledge of the exercise and its intended outcomes, such as the Exercise Controller or a designated representative.

Briefings can take place immediately before the exercise or during the preparation phase, provided there isn’t an extended gap that could cause attendees to forget critical information.

All briefings should follow the SMEACS format and, at a minimum, cover:

Exercise aim and objectives

Scenario overview (without revealing specific surprises or injects, unless essential for the group)

Relevant roles and responsibilities for the group being briefed

Copies of any relevant documents

### SMEAC Format

Situation: A summary of the current circumstances, including relevant background information and context.

Mission: A clear and concise statement of the task or objective to be achieved.

Execution: The plan detailing how the mission will be accomplished, outlining strategies, tactics, and specific tasks.

Administration and Logistics: Information on support elements such as resources, supplies, personnel, and logistical considerations necessary for the operation.

Command and Communications: Details about the command structure, reporting lines, and communication protocols to ensure coordination among all parties involved.

Safety: Identification of potential hazards and safety measures to protect personnel and assets during the operation.

## Exercise Termination

The exercise will formally conclude once the facilitator has completed the final phase of the scenario and the post-exercise debrief has been conducted.

The exercise is designed to run for a maximum duration of six hours. If the presentation is not completed within this timeframe, the Exercise Director may determine whether to conclude the activity at that point or extend the session to complete the remaining content.

## Public information

Responsibility for any media engagement during the exercise rests with the REMC. Where real or simulated media involvement is anticipated, it is recommended that the REMC engage an internal media representative or communications specialist to participate in both the planning and conduct phases, to ensure effective and coordinated media management.

In cases where combat and support agencies anticipate media engagement as part of their exercise roles, agency representatives should coordinate with their respective media departments and consider involving agency media personnel in the exercise.

Regardless of anticipated media activity, all participating organisations are advised to inform their internal media departments about the exercise to facilitate smooth communication and alignment.

## Evaluation Plan

### Purpose of Evaluation

The primary purpose of exercise evaluation is to assess both the effectiveness of the exercise and how well it met its stated aims and objectives.

A rigorous evaluation process enables planners and operational managers to systematically enhance future exercises, as well as related procedures, processes, and operational initiatives. Through observation, data collection, analysis, and reporting, evaluation transforms insights gained from the exercise into practical improvements for future operations.

Exercise evaluation involves a series of post-exercise activities focused on:

Gathering feedback and assessing the conduct of the exercise

Collecting insights on participant experiences

Evaluating the achievement of exercise objectives

Transferring lessons learned into lesson management systems

### Process of Evaluation

To facilitate a smooth and effective evaluation, an Exercise Evaluation Coordinator should be appointed prior to the exercise. The Coordinator’s primary role is to manage the overall evaluation process and lead the team of evaluators.

One or more evaluators should be appointed to assist with data collection and observation throughout the exercise. The number of evaluators required will depend on the exercise cohort size and the volume of data to be gathered. For smaller groups, the Exercise Coordinator may take on both evaluator and coordinator roles (see Attachment: EXCON Staff Responsibilities for the full list of Coordinator and Evaluator responsibilities).

### Data Collection & Observation

Data and observations will be gathered during and after the exercise using the following tools:

Participant Feedback Form

After-Action Review Debrief Forms

Evaluator’s Observation Checklist

Templates for these forms are provided in the Exercise Evaluation Plan. EXCON staff may implement additional data collection methods as appropriate.

### Data Analysis

Upon completing the exercise, evaluators will return all completed data collection tools to the Exercise Evaluation Coordinator. The Coordinator will then compile and analyse the collected data and observations, documenting insights and lessons in the analysis tables within the Evaluation Plan.

### Exercise Debriefs

An essential component of a successful exercise is the ability to debrief the activities of the conduct phase. A series of debriefs will be required at the conclusion of an exercise. Depending on the scale of the exercise these may include:

informal ‘hot’ debrief (immediately post-exercise) for:

Participants

EXCON

formal debriefs for:

organisation-specific debrief

a formal multi-organisation debriefs involving all participants and EXCON team members

exercise management debrief.

In all cases the debrief must be planned and communicated to all those who need to be involved.

During the debrief process, detailed information is collected at a lower level, with that information contributing to higher-level and subsequent debriefs.

Refer to the accompanying ‘Exercise Evaluation Plan’ for the AAR Debrief Observation Form.

### Exercise Report

Following data analysis, the Coordinator will prepare an exercise report on behalf of the Exercise Director, summarising key findings and lessons learned.

The final exercise and evaluation reports are to be submitted to the Premier’s Department and will contribute to the annual State Lessons Analysis process.

For a small exercise there may be one evaluator who produces a one-page report. For a large exercise there may be several individual evaluator reports that need to be analysed and summarised into the final exercise report.

The Exercise Evaluation Coordinator may be asked to draft the exercise report. Exercise reports should be produced to effect change and improvements. Reports do not have to be extensive to achieve that. Exercise reports should clearly identify areas or issues to be improved. They should include enough context for each issue or provide links to that context. If opportunities for improvement or recommendations are identified, they can be included.

The Exercise Director is responsible for finalising the exercise report and then sending it to those responsible for resolving the opportunities for improvement or recommendations that have been identified.

Refer to the accompanying ‘Exercise Evaluation Plan’ for the Exercise Report template.

Any collateral generated from the exercise (e.g., photos, videos, case studies) should also be provided to the Premier’s Department to support a shared resource cache for agency reference and use.

## Budget

This exercise will be funded through existing business as usual arrangements. The REMC and its member agencies and partners are responsible for meeting exercise related costs, as appropriate to their roles and participation. No dedicated funding has been allocated by the NSW Premier’s Department for this activity.

Costs are expected to be shared across participating agencies and partners, with contributions managed in line with local agreements and existing interagency support arrangements.

### Anticipated Expenses

Anticipated expenses associated with the conduct of the exercise may include, but not be limited to:

| Expense | Responsible Entity |
| --- | --- |
| Venue Hire | REMC |
| Catering | REMC |
| Staffing | Individual Agencies / Organisations |
| Travel & Accommodation | Individual Agencies / Organisations |
| Exercise Materials & Documentation | REMC |
| External Exercise Facilitator (if required) | REMC |

## Timeline

Outline the proposed timeline for the planning, conduct and evaluation of the exercise.

| Category | Responsible | Due by |
| --- | --- | --- |
| Concept | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |
| Planning | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |
| Conduct | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |
| Evaluation and reporting | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |

## Points of Contact

List key contact persons involved in the overall planning and coordination of this exercise.

Include person’s name, work area, phone and email.

| Name | Position | Contact Details |
| --- | --- | --- |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |

## Approval

| Approved / Not Approved | Approved / Not Approved |
| --- | --- |
| ______________________________ | ________________________________ |
| Name Title | Name Title |
| Date | Date |

## Attachments

### Exercise Outputs

The outputs from the exercise conduct and evaluation phases may include:

| Conduct Phase | Evaluation Phase |
| --- | --- |
| Participant learning Organisational learning REMC learning Debriefing Post exercise report Observations capture Lessons identified Procedure / tool evaluation | Exercise report Stakeholder feedback Inputs into lessons management processes Actions arising from exercise reports are passed to responsible individual / organisations |

### Exercise Program

| Date | Task |
| --- | --- |
| [INSERT DATE] | Exercise collateral developed |
| [INSERT DATE] | Expressions of interest open |
| [INSERT DATE] | Expressions of interest close |
| [INSERT DATE] | Exercises held |
| [INSERT DATE] | Acquittals including exercise and evaluation reports due |

### EXCON Staff Responsibilities

#### Exercise Director

Appoints Exercise Control Staff and Evaluation Coordinator

Facilitates exercise planning including time, date, style, scenario and scope

Facilitates development of all documents including Concept Plan, Master Schedule of Events, Risk Management Plan, Participant Instructions, Control Staff Instructions and Evaluation Plan

Ensures the exercise stays within scope

Coordinates the funding, resources, catering, and agencies

Authorises alterations to the planned program

Coordinates and prepares the Final Evaluation Report

Authorised person to start, suspend or conclude the exercise

#### Exercise Controller

Manages Master Schedule of Events for the exercise event site

Manages all Exercise activities relative to the exercise event site

Ensures adequate opportunities exist to achieve exercise and agency objectives

Manages safety and risk in accordance with approved plans

Simulates activities not performed by participants

Assists and contributes to debriefs

Contributes to the Exercise Evaluation Report

#### Exercise Planning Coordinator

Assists in the development of exercise objectives, scope, and scenarios

Supports the creation of key documents (Concept Plan, Master Schedule, Participant Instructions)

Identifies and assesses potential risks

Ensures all planning aligns with the exercise goals and maintains realistic scenarios

#### Exercise Facilitator

Leads the exercise discussion and guides participants through the scenario

Poses questions and prompts to encourage active engagement and critical thinking

Facilitates the delivery of the desktop-based functional components of the exercise.

Maintains the flow of the exercise, ensuring discussions stay within scope and timeframe

Provides clarifications on exercise scenarios and objectives as needed

Observes participant responses and interactions for evaluation purposes

Coordinates with the Exercise Controller on any required adjustments during the session

#### Exercise Evaluation Coordinator

Appoint and coordinate exercise evaluators

Provide briefings, guidance, and support to evaluators

Facilitate after-action reviews, including hot and formal debriefs

Collate feedback and evaluation reports from both participants and evaluators

Prepare the exercise evaluation report on behalf of the Exercise Director

#### Exercise Evaluators

Appointed by Exercise Evaluation Coordinator

Watches and listens to the exercise

Be fully briefed and know exercise objectives and key performance measures

Measures and evaluates the conduct and outcomes of exercise activities and records outcomes against specified performance measures

Makes notes to assist the debrief and Evaluation Report

Assists or leads the hot debrief for their agency after the exercise, as required

Assists and contributes to the formal debrief

#### Logistics Coordinator

Liaises with venue owners or operators

Coordinates catering and welfare requirements

Arranges transport of participants and equipment

Commissions preparation of tools, resources and documents required for the exercise

Procures additional equipment, consumables, and resources, as required

Sets up registration or administration areas for exercise control.

[INSERT ADDITIONAL RESPONSIBILITIES AS REQUIRED]

### Exercise Briefings and Debriefings

#### Briefings

Use the table below to document each planned briefing, specifying the type of briefing, target audience, presenter, and scheduled timing. This will help ensure all briefings are organised and delivered as planned.

| Briefing Type | Target Audience | Presenter | Scheduled Timing |
| --- | --- | --- | --- |
| eg. Pre-Exercise Briefing | All participants | John Smith | Immediately before exercise |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |

All briefings should be delivered using the SMEACS briefing format

| Section | Content |
| --- | --- |
| Situation | Provide a brief overview of the current situation or context that necessitates action or response. eg; "A fire has broken out in the facility’s kitchen area, requiring an evacuation and activation of emergency response procedures." |
| Mission | Clearly state the objective or purpose of the operation or response. eg: "The mission is to ensure all personnel evacuate safely and assess the effectiveness of emergency response procedures." |
| Execution | Outline specific tasks, roles, and the sequence of actions expected to achieve the mission. eg: "Personnel will follow assigned evacuation routes, report to assembly points, and respond to communications from the control team." |
| Administration & Logistics | Detail logistical arrangements, including available resources, equipment, and other support requirements. eg: "The designated assembly area will be in the parking lot, with first aid kits and radios distributed to team leaders." |
| Command & Control | Define who is in charge, clarify the command structure, and specify reporting lines and communication protocols. eg: "The Incident Commander is in charge; all team leaders report to them, and communication will occur over designated radio channels." |
| Safety | Highlight safety precautions, potential risks, and any procedures to ensure participant safety. eg: "Use marked evacuation routes only. The term ‘No Duff’ will be used to indicate a real emergency. First aid is available on-site if needed." |

#### Debriefs

Use the table below to document each planned debrief, specifying the type of debrief, target audience, presenter, and scheduled timing. This will help ensure all debriefs are organised and delivered as planned.

| Debrief Type | Target Audience | Presenter | Scheduled Timing |
| --- | --- | --- | --- |
| eg. Hot AAR Debrief | Exercise participants | John Smith | Immediately after exercise termination |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |

### Roles & Responsibilities Checklist

| Role | Checklist |
| --- | --- |
| Exercise Director | Before Exercise - Approve exercise aim, objectives, and key documentation. - Confirm and authorise budget and resources with stakeholders. - Appoint and authorise all EXCON roles, including the Exercise Facilitator. - Finalise and communicate the exercise date, time, and venue to all stakeholders. - Confirm communication protocols with key stakeholders and external agencies to ensure alignment. - Review the scenario with the Exercise Planning Coordinator. - Schedule a high-level briefing for senior leaders or stakeholders on objectives, scenario, and expected outcomes. - Authorise any required changes to the exercise program or plan. During Exercise - Authorise commencement, termination, or suspension of the exercise as needed. - Supervise the conduct phase to ensure alignment with objectives. - Monitor participant engagement and authorise adjustments as necessary. - Coordinate real-time adjustments with EXCON and facilitators as needed. After Exercise - Confirm that debriefs and evaluation processes are completed. - Review, approve, and submit the final exercise report to the Premier’s Department, ensuring all findings and recommendations are included. - Verify that all funding reimbursement requests and required documentation are submitted to the relevant authorities. [Insert additional items as required] |
| Exercise Controller | Before Exercise - Review and understand the Exercise Scenario and timing of activities. - Confirm site-specific activities align with objectives and ensure resources are prepared. - Familiarise yourself with the safety and risk management plan. - Plan and prepare simulations for non-participant activities as required. - Ensure all relevant parties are briefed, delivering pre-exercise briefings if needed. During Exercise - Oversee and manage the timing and execution of the exercise, adjusting as necessary. - Monitor exercise activities to ensure alignment with objectives, adjusting flow as needed. - Actively manage site safety, responding to incidents according to the risk plan. - Simulate activities not performed by participants as required. - Facilitate participant engagement to meet exercise and agency objectives. After Exercise - Participate in debrief sessions, providing feedback on exercise flow and participant engagement. - Contribute observations and insights to the Exercise Evaluation Report. - Complete and submit safety and incident reports for any incidents during the exercise. - Assist in facilitating and leading debriefs as needed. [Insert additional items as required] |
| Exercise Planning Coordinator | Before Exercise - Develop and finalise the detailed exercise plan. - Confirm roles, responsibilities, and appointments within the EXCON structure. - Finalise all required documents (evaluation plans, injects, scenarios). - Complete the scenario and injects, ensuring all elements are fully developed and aligned with objectives. - Distribute essential documents (e.g. exercise plans, participant handbooks, role assignments) to all participants and controllers in advance. - Coordinate pre-exercise briefings and distribute exercise materials. - Establish and confirm a clear communication plan among participants, EXCON, and evaluators. - Conduct a risk assessment and prepare necessary documentation. During Exercise - Coordinate with the Exercise Controller on inject timings and scenario adjustments as needed. After Exercise - Participate in debrief and evaluation processes. [Insert additional items as required] |
| Exercise Facilitator | Before Exercise - Review the scenario, objectives, and prompts to guide participant discussions. - Review the exercise presentation and suggest any necessary changes or updates. During Exercise - Lead discussions and guide participants through each scenario phase. - Pose questions and prompts to encourage engagement and critical thinking. - Facilitate the delivery of the desktop-based functional components of the exercise. - Keep discussions on track, within scope, and aligned with the exercise timeframe. - Provide clarifications on scenarios and objectives as needed. - Coordinate with the Exercise Controller on any necessary adjustments. After Exercise - Contribute observations and insights to debrief and evaluation processes. [Insert additional items as required] |
| Exercise Evaluation Coordinator | Before Exercise - Assign evaluators to specific exercise components, ensuring full coverage. - Brief and train evaluators on observation techniques and assessment criteria. - Distribute evaluation tools, including observation templates and data collection methods. - Conduct a pre-exercise calibration meeting to review objectives, standards, and scoring criteria. - Prepare feedback mechanisms (e.g. feedback forms, debrief sessions) for gathering insights. - Identify key observation points at the venue and station evaluators strategically. During Exercise - Support and coordinate evaluators, providing resources and assistance as needed. - Oversee observation collection to ensure validity and consistency with evaluation standards. After Exercise - Ensure after-action reviews (AARs) and debriefs are conducted, leading them as required. - Collate and analyse evaluator reports to identify key findings and improvement areas. - Draft the final exercise report, consolidating observations, feedback, and recommendations. [Insert additional items as required] |
| Exercise Evaluators | Before Exercise - Review exercise objectives, evaluation criteria, and assigned focus areas. - Familiarise yourself with observation tools and data collection methods. During Exercise - Observe participant actions and interactions according to assigned objectives. - Record observations accurately, focusing on outcomes relevant to exercise performance measures. - Coordinate with the Evaluation Coordinator for any needed clarification or guidance. After Exercise - Conduct debriefs as required. - Submit completed observation notes and any supporting documentation. - Participate in debrief sessions, sharing insights and feedback on observations. [Insert additional items as required] |
| Logistics Coordinator | Before Exercise - Book the venue, ensuring it meets all setup requirements. - Arrange catering based on participant needs and confirm service details. - Send invites and agendas to all participants with event details and expectations. - Confirm all technical requirements (audio-visual aids, communication devices). - Prepare props, special equipment and documents needed for the exercise. - Visit the venue to confirm setup, ensuring equipment (e.g. projectors, seating, staging areas) is in place. - Arrange clear signage to direct participants, observers, and evaluators to appropriate areas. - Arrange inventory supplies, such as name badges, safety equipment, notepads, and pens. - Confirm transportation and parking arrangements, providing relevant information to participants. During Exercise - Open and prepare the venue, ensuring all areas are ready for use. - Confirm catering has arrived, is laid out, and is maintained throughout the event. - Address any logistical needs as they arise to support the smooth flow of activities. After Exercise - Participate in debrief sessions, providing insights on logistics and venue setup. - Contribute feedback and observations to the evaluation report. [Insert additional items as required] |