# Exercise Plan

Major Power Outage Exercise - Functional

Contents

Exercise Plan 1

Exercise [Name] - Exercise Plan 4

Background 4

Need 4

Overview 4

Participants 5

Exercise Aim and Objectives 5

Aim 5

Exercise Objectives & Performance Measures 5

Exercise Scope 7

Exercise Outline 8

Exercise Name 8

Exercise Type 8

Scenario 9

Proposed delivery 9

Governance and Management Structure 9

Exercise Planning Group 9

Exercise Participants 9

Exercise Control 10

Exercise Briefings 10

SMEAC Format 11

Exercise Termination 11

Public information 12

Evaluation Plan 12

Purpose of Evaluation 12

Process of Evaluation 12

Data Collection & Observation 13

Data Analysis 13

Exercise Debriefs 13

Exercise Report 13

Budget 14

Anticipated Expenses 14

Timeline 15

Points of Contact 15

Approval 15

Attachments 16

Exercise Outputs 16

Exercise Program 16

EXCON Staff Responsibilities 17

Exercise Briefings and Debriefings 19

Roles & Responsibilities Checklist 21

## Exercise [Name] - Exercise Plan

### Background

Electricity underpins the operation of critical infrastructure, essential services, and everyday community life across New South Wales. A prolonged and widespread electricity supply disruption has the potential to create cascading impacts across critical systems, essential services, and everyday community functions.

While the New South Wales electricity network is designed with safeguards and redundancies, it remains vulnerable to major incidents. Extreme weather, infrastructure failure, supply shortages, or malicious acts can all result in significant disruption. Recent outage emergencies in Far West NSW and the Hunter have demonstrated the severe consequences of extended electricity loss, including telecommunications failures, difficulties in accessing essential goods and services, and disproportionate impacts on vulnerable and remote communities.

The NSW State Electricity Supply Emergency Sub Plan and the Energy and Utility Services Supporting Plan provide the framework for managing such events. This exercise has been developed to strengthen local and regional arrangements by testing decision-making, coordination, and consequence management in response to a prolonged, widespread electricity supply disruption.

### Need

There is a need to test and validate the capability of Regional and Local Emergency Operations Centres (REOC/LEOC), under the coordination of Regional and Local Emergency Controllers (REOCON/LEOCON), to manage the consequences of a prolonged, widespread electricity supply disruption. This need arises from recent large-scale outages in New South Wales, which exposed vulnerabilities in service continuity, community communication, and welfare support, particularly for vulnerable and remote populations.

Specific areas of focus include:

- Examining the effectiveness of arrangements for maintaining critical services such as health, telecommunications, food, water, and fuel supply.

- Exploring the effectiveness of public communication and community reassurance strategies under conditions of prolonged uncertainty.

- Testing decision-making processes and escalation pathways when information on energy supply and reliability is incomplete, delayed, or inconsistent.

- Evaluating welfare and support arrangements for vulnerable and geographically isolated communities.

### Overview

This exercise will provide insights into the challenges of managing the consequences of a prolonged, widespread electricity supply disruption. It will examine decision-making, governance, continuity of critical services, provision of welfare support, and emergency operations functionality in the context of significant power and communication constraints.

The primary target audience for this exercise is REOCs and LEOCs and their members.

## Participants

Participants in this exercise will include members of the REOC / LEOC and representatives from participating organisations as defined in the area’s Regional or Local Emergency Management Plan (REMP / LEMP). Participants may include, but are not limited to:

Regional Emergency Operations Controller (REOCON) and Local Emergency Operations Controller (LEOCON)

Regional Emergency Management Officer (REMO) and Local Emergency Management Officer (LEMO)

REMC / LEMC Combat and Supporting Agency Representatives, as relevant to the area, including:

NSW Police Force

NSW Ambulance

NSW Rural Fire Service

Fire & Rescue NSW

NSW State Emergency Service

Marine Rescue NSW

VRA Rescue

Surf Life Saving NSW

Functional Area Coordinators and Representatives

Other Stakeholders as deemed appropriate by the REMC / LEMC

## Exercise Aim and Objectives

### Aim

To strengthen the planning, preparedness, and coordination of REOCs and LEOCs in managing the consequences of a prolonged, widespread electricity supply disruption in NSW. The exercise will test decision-making, interagency coordination, continuity of critical services, community communication, delivery of welfare support, and assistance to vulnerable populations, in alignment with the NSW Energy and Utility Services Supporting Plan and the State Electricity Supply Emergency Sub-Plan.

[Insert additional or alternate aim as required]

### Exercise Objectives & Performance Measures

Test how effectively REOCs and LEOCs coordinate with the Energy and Utility Services Functional Area (EUSFA), local councils, emergency services, and other agencies in managing the consequences of a prolonged electricity supply disruption.

- An appropriate schedule of liaison and coordination meetings is established and maintained in a timely manner.

- Interagency coordination meetings are convened promptly within the exercise scenario timeframe.

- Decisions are escalated to the appropriate authority within appropriate timeframes.

- Communication flows between stakeholders, including committees, councils, EOCs, and agencies, are timely and accurate.

- Participants demonstrate collaborative problem-solving when faced with conflicting or competing priorities.

[Insert additional standard measures as required]

Test arrangements to maintain and restore essential community services, including health, water, fuel, food, telecommunications, and public information, during extended power outages, with particular attention to infrastructure interdependencies..

- Disruptions to essential services are identified and prioritised in a timely manner.

- Plans to restore or re-establish essential services are developed and communicated within expected timeframes.

- Continuity arrangements for at least two critical services are activated in accordance with existing plans.

- Public information messages are drafted and disseminated through appropriate channels (simulated), reflecting service constraints.

- Participants identify and respond effectively to cascading impacts and competing priorities.

[Insert additional standard measures as required]

Test the adequacy of arrangements for providing timely welfare assistance, relief services, and community support to affected populations during prolonged disruptions.

- Welfare needs are identified and prioritised in a timely manner in accordance with relevant plans and procedures.

- Plans for the provision of welfare support are developed and communicated appropriately within required timeframes.

- Welfare support requests and arrangements are coordinated and communicated through the appropriate channels.

- Welfare centre activation requirements are considered and actioned within relevant timelines.

- Information on welfare services is communicated clearly to affected communities during the scenario.

[Insert additional standard measures as required]

Assess how agencies identify, prioritise, and provide targeted support to vulnerable groups and individuals, including those reliant on medical equipment, Aboriginal communities, and geographically isolated populations, during a prolonged power outage.

- Vulnerable groups and individuals are identified in a timely manner during the exercise scenario.

- Action plans to address the critical needs of vulnerable groups and individuals are developed and communicated within appropriate timeframes.

- Requests for specialised support for vulnerable groups and individuals are escalated and actioned appropriately within expected timelines.

- Aboriginal communities and remote towns are explicitly included in planning discussions and operational responses.

- Information to vulnerable groups is tailored and delivered via appropriate channels, reflecting the service constraints of the scenario.

[Insert additional standard measures as required]

Evaluate how REOCs, LEOCs, and supporting agencies make and escalate decisions when operating with incomplete, delayed, or inconsistent information from energy providers and other sources.

- Breakdowns or gaps in communication and information sharing are identified and acted upon in a timely manner.

- Mechanisms for decision-making with incomplete or inconsistent information are demonstrated by incident response leaders.

- Uncertainty and information gaps are acknowledged explicitly in decision-making discussions and briefings.

[Insert additional standard measures as required]

## Exercise Scope

This exercise involves members of the REOC or LEOC, and supporting agencies, as defined in the relevant REMP / LEMP. It is structured as a six-hour, functional activation style exercise designed to test and validate decision-making, governance, coordination, and consequence management arrangements in response to a prolonged, widespread electricity supply disruption. The scenario will centre on the cascading community impacts of extended power and communication outages.

The exercise is intended for application at the regional or local level and reflects the scope and responsibilities of REOCs and LEOCs in managing the consequences of major electricity outages. It has been deliberately designed to be non-specific to any single geographic area, ensuring it can be delivered consistently across all regions of New South Wales. The exercise includes the actual establishment of an Emergency Operations Centre (EOC).

In Scope:

REOC / LEOC level decision-making and coordination activities.

Physical activation or setup of an EOC.

Governance and liaison arrangements with EUSFA and other agencies.

●	Identification and prioritisation of critical service continuity.

●	Coordination of welfare support and assistance to vulnerable and remote communities.

● 	Public information and communication strategies under conditions of uncertainty.

● 	Documentation and observation of decisions made for exercise evaluation purposes.

Out of Scope:

Operational field management of power network restoration.

Real-time service delivery, logistics, or resource deployment.

Involvement of the general public or industry operators beyond their representative roles in the exercise.

Testing of agency-specific internal procedures not directly related to REOC / LEOC coordination or consequence management.

## Exercise Outline

### Exercise Name

[To be determined by the relevant LEMC/REMC]

### Exercise Type

This exercise will be conducted as a functional activation-style exercise, designed to test and practise REOC/LEOC coordination, communication, and support functions in the context of an EOC operation, alongside a simulated IMT, during a simulated emergency. Participants will respond in real time to scenario information, presented as it would be during an actual emergency, using established communication channels such as phone, email, or web-based incident management systems.

To support the exercise, a set of suggested general ideas, special ideas, and injects has been provided. These elements serve as a foundation for structuring the exercise and guiding the activities of EOCs. Individual LEMCs and REMCs are encouraged to tailor these concepts to reflect their specific community characteristics, risks, and resources. Organisers should establish a robust activation cell to simulate the roles of an IMT, agency staff, community members, and other stakeholders. This ensures participants are provided with realistic injects and prompts, enhancing the realism and engagement of the exercise.

The flow of the exercise will be managed by the Exercise Control (EXCON) team under the direction of the exercise controller. Scenario injects will be delivered in accordance with the Master Schedule of Events (MSE), simulating the evolving nature of a power outage emergency. The pace of the exercise can be adjusted as needed to maintain engagement and align with exercise objectives.

Functional activation exercises are particularly effective for testing the readiness and adaptability of RECCs and LEOCs. This exercise format enables participants to:

- Practice decision-making and procedural application in a controlled, simulated environment.

- Assess the interaction of EOCs with external agencies and stakeholders.

- Focus on coordination and control without requiring the deployment of external field resources.

This format provides a cost-effective way to evaluate real-time emergency management performance, offering a high level of realism and an opportunity to enhance preparedness across all levels of coordination.

To ensure relevance, organisers are encouraged to tailor the provided general ideas, special ideas, and injects to reflect the unique risks, infrastructure, and community characteristics of their region. This may include incorporating local maps, specific geographic features, and community-specific vulnerabilities into the scenario. Organisers should also adapt the activation cell structure to include key local stakeholders, such as representatives from community groups, major industries, or high-risk facilities, to simulate realistic interactions and decision-making.

### Scenario

The exercise scenario is set in late summer in New South Wales, against the backdrop of unsettled and severe weather across the region. A series of damaging storms has caused extensive damage to critical electricity distribution and transmission infrastructure, cutting power to large areas and triggering a cascade of prolonged community consequences.

The scenario provides a realistic context for participants to test coordination, governance, and decision-making processes, as well as the challenges associated with managing a major, protracted power outage.

### Proposed delivery

The exercise is proposed for delivery on [DATE] at [VENUE].

The exercise will be conducted by a suitably experienced Exercise Control Team appointed by the exercise planning group.

The attached facilitators guide, and resources are to be used to conduct the exercise.

## Governance and Management Structure

### Exercise Planning Group

An exercise planning group will be established to lead the planning and preparation of the exercise. This group should include:

- Representatives from the REMC / LEMC

- Combat and supporting agencies

- Representatives from EUSFA

- Experienced exercise planning and facilitation specialist/s

- Other key stakeholders as required

The planning group will be chaired by [INSERT NAME] from [INSERT AGENCY NAME].

### Exercise Participants

Proposed agencies/participants:

- Members of the REOC / LEOC, including but not limited to REOCON, LEOCON, and agency representatives

- Regional Emergency Management Officers (REMO) and Emergency Management Officers (LEMO)

- State Government Combat and Support Agencies

- Functional Area Coordinators and/or Functional Area Representatives

Agencies who will be participating in the exercise include:

[INSERT NAMES OF PARTICIPATING AGENCIES]

### Exercise Control

An Exercise Control (EXCON) Group will be established for the purpose of running and facilitating the exercise.

EXCON Roles are listed below. See appendix below for responsibilities of each of the below roles.

| Role | Assignee |
| --- | --- |
| Exercise Director | [INSERT NAME] |
| Exercise Planning Coordinator | [INSERT NAME] |
| Exercise Controller | [INSERT NAME] |
| Logistics Coordinator | [INSERT NAME] |
| Exercise Evaluation Coordinator | [INSERT NAME] |
| Exercise Evaluators | [INSERT NAME/S] |
| Activation Cell Coordinator | [INSERT NAME] |
| Activation Cell Members | [INSERT NAME/S] |
| Observer Coordinator | [INSERT NAME] |
| Safety Officer | [INSERT NAME] |

### Exercise Briefings

Before beginning the exercise, the following groups should be briefed:

Participants

Evaluators

Additional briefings may also be necessary, depending on the exercise setup:

Safety Briefing

Observer Briefing

Activation Cell Briefing

Briefings should be delivered by someone with in-depth knowledge of the exercise and its intended outcomes, such as the Exercise Controller or a designated representative.

Briefings can take place immediately before the exercise or during the preparation phase, provided there isn’t an extended gap that could cause attendees to forget critical information.

All briefings should follow the SMEACS format and, at a minimum, cover:

Exercise aim and objectives

Scenario overview (without revealing specific surprises or injects, unless essential for the group)

Relevant roles and responsibilities for the group being briefed

Copies of any relevant documents

### SMEAC Format

Situation: A summary of the current circumstances, including relevant background information and context.

Mission: A clear and concise statement of the task or objective to be achieved.

Execution: The plan detailing how the mission will be accomplished, outlining strategies, tactics, and specific tasks.

Administration and Logistics: Information on support elements such as resources, supplies, personnel, and logistical considerations necessary for the operation.

Command and Communications: Details about the command structure, reporting lines, and communication protocols to ensure coordination among all parties involved.

Safety: Identification of potential hazards and safety measures to protect personnel and assets during the operation.

## Exercise Termination

The exercise will conclude under the direction of the Exercise Controller, who will declare the official end of the exercise using the term ENDEX. This will occur when the exercise has reached the planned end of the scenario injects or when the Exercise Controller determines that sufficient objectives have been met. The exercise is anticipated to run for 4-6 hours.

Criteria for Exercise Termination:

- Completion of Scenario Injects: The exercise will conclude once all planned scenario injects have been delivered and addressed by participants, even if the simulated scenario timeline extends beyond the exercise duration.

- Sufficient Progress: The Exercise Controller may decide to end the exercise early if participants have sufficiently engaged with the scenario and injects, gaining valuable insights and achieving the exercise's primary objectives within the expected timeframe.

- Real-World Incident (No Duff): If an actual emergency or significant incident occurs requiring the attention of participants, the Exercise Controller will immediately halt the exercise, declare a "No Duff" incident, and formally terminate the exercise to ensure participants can respond to the real-world event.

Post-Termination Activities:

Following ENDEX, participants and EXCON team members will transition to post-exercise activities, including initial debriefs and logistical tasks such as restoring the exercise site to its pre-exercise state. These activities will be managed collaboratively by relevant EXCON roles under the direction of the Exercise Controller.

## Public information

Responsibility for any media engagement during the exercise rests with the REMC / LEMC. Where real or simulated media involvement is anticipated, it is recommended that the REMC or LEMC engage an internal media representative or communications specialist to participate in both the planning and conduct phases, to ensure effective and coordinated media management.

In cases where combat and support agencies anticipate media engagement as part of their exercise roles, agency representatives should coordinate with their respective media departments and consider involving agency media personnel in the exercise.

Regardless of anticipated media activity, all participating organisations are advised to inform their internal media departments about the exercise to facilitate smooth communication and alignment.

## Evaluation Plan

### Purpose of Evaluation

The primary purpose of exercise evaluation is to assess both the effectiveness of the exercise and how well it met its stated aims and objectives.

A rigorous evaluation process enables planners and operational managers to systematically enhance future exercises, as well as related procedures, processes, and operational initiatives. Through observation, data collection, analysis, and reporting, evaluation transforms insights gained from the exercise into practical improvements for future operations.

Exercise evaluation involves a series of post-exercise activities focused on:

Gathering feedback and assessing the conduct of the exercise

Collecting insights on participant experiences

Evaluating the achievement of exercise objectives

Transferring lessons learned into lesson management systems

### Process of Evaluation

To facilitate a smooth and effective evaluation, an Exercise Evaluation Coordinator should be appointed prior to the exercise. The Coordinator’s primary role is to manage the overall evaluation process and lead the team of evaluators.

One or more evaluators should be appointed to assist with data collection and observation throughout the exercise. The number of evaluators required will depend on the exercise cohort size and the volume of data to be gathered. For smaller groups, the Exercise Coordinator may take on both evaluator and coordinator roles (see Attachment: EXCON Staff Responsibilities for the full list of Coordinator and Evaluator responsibilities).

### Data Collection & Observation

Data and observations will be gathered during and after the exercise using the following tools:

Participant Feedback Form

After-Action Review Debrief Forms

Evaluator’s Observation Checklist

Templates for these forms are provided in the Exercise Evaluation Plan. EXCON staff may implement additional data collection methods as appropriate.

### Data Analysis

Upon completing the exercise, evaluators will return all completed data collection tools to the Exercise Evaluation Coordinator. The Coordinator will then compile and analyse the collected data and observations, documenting insights and lessons in the analysis tables within the Evaluation Plan.

### Exercise Debriefs

An essential component of a successful exercise is the ability to debrief the activities of the conduct phase. A series of debriefs will be required at the conclusion of an exercise. Depending on the scale of the exercise these may include:

informal ‘hot’ debrief (immediately post-exercise) for:

Participants

EXCON

formal debriefs for:

organisation-specific debrief

a formal multi-organisation debriefs involving all participants and EXCON team members

exercise management debrief.

In all cases the debrief must be planned and communicated to all those who need to be involved.

During the debrief process, detailed information is collected at a lower level, with that information contributing to higher-level and subsequent debriefs.

Refer to the accompanying ‘Exercise Evaluation Plan’ for the AAR Debrief Observation Form.

### Exercise Report

Following data analysis, the Coordinator will prepare an exercise report on behalf of the Exercise Director, summarising key findings and lessons learned.

The final exercise and evaluation reports are to be submitted to the Premier’s Department and will contribute to the annual State Lessons Analysis process.

For a small exercise there may be one evaluator who produces a one-page report. For a large exercise there may be several individual evaluator reports that need to be analysed and summarised into the final exercise report.

The Exercise Evaluation Coordinator may be asked to draft the exercise report. Exercise reports should be produced to effect change and improvements. Reports do not have to be extensive to achieve that. Exercise reports should clearly identify areas or issues to be improved. They should include enough context for each issue or provide links to that context. If opportunities for improvement or recommendations are identified, they can be included.

The Exercise Director is responsible for finalising the exercise report and then sending it to those responsible for resolving the opportunities for improvement or recommendations that have been identified.

Refer to the accompanying ‘Exercise Evaluation Plan’ for the Exercise Report template.

Any collateral generated from the exercise (e.g., photos, videos, case studies) should also be provided to the Premier’s Department to support a shared resource cache for agency reference and use.

## Budget

This exercise will be funded through existing business as usual arrangements. The REMC or LEMC and its member agencies and partners are responsible for meeting exercise related costs, as appropriate to their roles and participation.

Costs are expected to be shared across participating agencies and partners, with contributions managed in line with local agreements and existing interagency support arrangements.

In FY25/26, the Emergency Management Exercise Program administered by the Premier’s Department makes funding available to LEMCs and REMCs for eligible ancillary costs associated with this exercise. Further information is available within the Program Guidelines.

### Anticipated Expenses

Anticipated expenses associated with the conduct of the exercise may include, but not be limited to:

| Expense | Responsible Entity |
| --- | --- |
| Venue Hire | REMC / LEMC |
| Catering | REMC / LEMC |
| Staffing | Individual Agencies / Organisations |
| Travel & Accommodation | Individual Agencies / Organisations |
| Exercise Materials & Documentation | REMC / LEMC |
| External Exercise Facilitator (if required) | REMC / LEMC |

## Timeline

Outline the proposed timeline for the planning, conduct and evaluation of the exercise.

| Category | Responsible | Due by |
| --- | --- | --- |
| Concept | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |
| Planning | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |
| Conduct | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |
| Evaluation and reporting | [INSERT NAME OF RESPONSIBLE PERSON] | [INSERT DUE DATE] |

## Points of Contact

List key contact persons involved in the overall planning and coordination of this exercise.

Include person’s name, work area, phone and email.

| Name | Position | Contact Details |
| --- | --- | --- |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |
| [INSERT NAME] | [INSERT POSITION] | [INSERT CONTACT DETAILS] |

## Approval

| Approved / Not Approved | Approved / Not Approved |
| --- | --- |
| ______________________________ | ________________________________ |
| Name Title | Name Title |
| Date | Date |

## Attachments

### Exercise Outputs

The outputs from the exercise conduct and evaluation phases may include:

| Conduct Phase | Evaluation Phase |
| --- | --- |
| Participant learning Organisational learning REMC / LEMC learning Debriefing Post exercise report Observations capture Lessons identified Procedure / tool evaluation | Exercise report Stakeholder feedback Inputs into lessons management processes Actions arising from exercise reports are passed to responsible individual / organisations |

### FY25/26 Emergency Management Exercise Program Key Dates

For LEMCs and REMCs that receive funding from the Premier’s Department to support delivery of this exercise, the following key dates should be noted:

| Date | Task |
| --- | --- |
| 1 August 2025 | Expressions of interest for funding open |
| 1 June 2026 | Expressions of interest close |
| 12 June 2026 | Reimbursement invoices due to Premier’s Department |
| 1 August 2025 – 30 June 2026 | Exercises held |
| 31 July 2026 | Exercise evaluation reports and collateral due to Premier’s Department |

### EXCON Staff Responsibilities

#### Exercise Director

Appoints Exercise Control Staff and Evaluation Coordinator

Facilitates exercise planning including time, date, style, scenario and scope

Facilitates development of all documents including Concept Plan, Master Schedule of Events, Risk Management Plan, Participant Instructions, Control Staff Instructions and Evaluation Plan

Ensures the exercise stays within scope

Coordinates the funding, resources, catering, and agencies

Authorises alterations to the planned program

Coordinates and prepares the Final Evaluation Report

Authorised person to start, suspend or conclude the exercise

#### Exercise Planning Coordinator

Assists in the development of exercise objectives, scope, and scenarios

Supports the creation of key documents (Concept Plan, Master Schedule, Participant Instructions)

Identifies and assesses potential risks

Ensures all planning aligns with the exercise goals and maintains realistic scenarios

#### Exercise Controller

Manages Master Schedule of Events for the exercise event site

Manages all Exercise activities relative to the exercise event site

Ensures adequate opportunities exist to achieve exercise and agency objectives

Manages safety and risk in accordance with approved plans

Simulates activities not performed by participants

Assists and contributes to debriefs

Contributes to the Exercise Evaluation Report

#### Logistics Coordinator

Liaises with venue owners or operators

Coordinates catering and welfare requirements

Arranges transport of participants and equipment

Commissions preparation of tools, resources and documents required for the exercise

Procures additional equipment, consumables, and resources, as required

Sets up registration or administration areas for exercise control.

#### Exercise Evaluation Coordinator

Appoint and coordinate exercise evaluators

Provide briefings, guidance, and support to evaluators

Facilitate after-action reviews, including hot and formal debriefs

Collate feedback and evaluation reports from both participants and evaluators

Prepare the exercise evaluation report on behalf of the Exercise Director

#### Exercise Evaluators

Appointed by Exercise Evaluation Coordinator

Watches and listens to the exercise

Be fully briefed and know exercise objectives and key performance measures

Measures and evaluates the conduct and outcomes of exercise activities and records outcomes against specified performance measures

Makes notes to assist the debrief and Evaluation Report

Assists or leads the hot debrief for their agency after the exercise, as required

Assists and contributes to the formal debrief

#### Activation Cell Coordinator

Monitors the progress of the Master Schedule of Events (MSE)

Introduces scenario injects as planned or directed by the Exercise Controller

Tracks participant responses to ensure alignment with exercise objectives

Simulates actions or decisions of organisations not participating in the exercise

Provides situational updates to the Exercise Controller as required

#### Activation Cell Member

Operate phones, radios, and messaging channels to simulate realistic communications during the exercise.

Role-play external stakeholders, agencies, organisations, and community members as directed by the Activation Cell Coordinator.

Deliver exercise injects in line with the Master Schedule of Events, ensuring consistency and realism.

Respond to participant enquiries and communications in accordance with scripted exercise information.

- Escalate issues, clarifications, or unscripted developments to the Activation Cell Coordinator promptly.

Maintain accurate records of communications and inject delivery for evaluation purposes.

- ● 	Contribute to hot and cold debriefs, providing insights on exercise flow, realism, and participant responses.

#### Observer Coordinator

Welcomes and briefs observers on the exercise scenario, objectives, and observation protocols.

Hosts and guides observers, ensuring safe access to designated areas without disrupting play.

Provides observer packs/materials and remains their main point of contact during the exercise.

Collects observer feedback and contributes key insights to debriefs and reporting.

#### Safety Officer

Monitors real-world safety and WHS risks throughout the exercise.

Ensures all activities comply with approved safety plans and procedures.

Intervenes promptly to address unsafe practices or conditions.

Provides safety briefings and supports debriefs with WHS observations.

[INSERT ADDITIONAL RESPONSIBILITIES AS REQUIRED]

### Exercise Briefings and Debriefings

#### Briefings

Use the table below to document each planned briefing, specifying the type of briefing, target audience, presenter, and scheduled timing. This will help ensure all briefings are organised and delivered as planned.

| Briefing Type | Target Audience | Presenter | Scheduled Timing |
| --- | --- | --- | --- |
| eg. Pre-Exercise Briefing | All participants | John Smith | Immediately before exercise |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT BRIEFING TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |

All briefings should be delivered using the SMEACS briefing format

| Section | Content |
| --- | --- |
| Situation | Provide a brief overview of the current situation or context that necessitates action or response. eg; "A fire has broken out in the facility’s kitchen area, requiring an evacuation and activation of emergency response procedures." |
| Mission | Clearly state the objective or purpose of the operation or response. eg: "The mission is to ensure all personnel evacuate safely and assess the effectiveness of emergency response procedures." |
| Execution | Outline specific tasks, roles, and the sequence of actions expected to achieve the mission. eg: "Personnel will follow assigned evacuation routes, report to assembly points, and respond to communications from the control team." |
| Administration & Logistics | Detail logistical arrangements, including available resources, equipment, and other support requirements. eg: "The designated assembly area will be in the parking lot, with first aid kits and radios distributed to team leaders." |
| Command & Control | Define who is in charge, clarify the command structure, and specify reporting lines and communication protocols. eg: "The Incident Commander is in charge; all team leaders report to them, and communication will occur over designated radio channels." |
| Safety | Highlight safety precautions, potential risks, and any procedures to ensure participant safety. eg: "Use marked evacuation routes only. The term ‘No Duff’ will be used to indicate a real emergency. First aid is available on-site if needed." |

#### Debriefs

Use the table below to document each planned debrief, specifying the type of debrief, target audience, presenter, and scheduled timing. This will help ensure all debriefs are organised and delivered as planned.

| Debrief Type | Target Audience | Presenter | Scheduled Timing |
| --- | --- | --- | --- |
| eg. Hot AAR Debrief | Exercise participants | John Smith | Immediately after exercise termination |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |
| [INSERT DEBRIEF TYPE] | [INSERT TARGET AUDIENCE] | [INSERT PRESENTER NAME] | [INSERT SCHEDULED TIMING] |

### Roles & Responsibilities Checklist

| Role | Checklist |
| --- | --- |
| Exercise Director | Before Exercise - Approve exercise aim, objectives, and key documentation. - Confirm and authorise budget and resources with stakeholders. - Appoint and authorise all EXCON roles, including the Exercise Facilitator. - Finalise and communicate the exercise date, time, and venue to all stakeholders. - Confirm communication protocols with key stakeholders and external agencies to ensure alignment. - Review the scenario with the Exercise Planning Coordinator. - Schedule a high-level briefing for senior leaders or stakeholders on objectives, scenario, and expected outcomes. - Authorise any required changes to the exercise program or plan. During Exercise - Authorise commencement, termination, or suspension of the exercise as needed. - Supervise the conduct phase to ensure alignment with objectives. - Monitor participant engagement and authorise adjustments as necessary. - Coordinate real-time adjustments with EXCON and facilitators as needed. After Exercise - Confirm that debriefs and evaluation processes are completed. - Review, approve, and submit the final exercise report to the Premier’s Department, ensuring all findings and recommendations are included. - Verify that all funding reimbursement requests and required documentation are submitted to the Premier’s Department, and other relevant authorities as required. [Insert additional items as required] |
| Exercise Controller | Before Exercise - Review and understand the Exercise Scenario and timing of activities. - Confirm site-specific activities align with objectives and ensure resources are prepared. - Familiarise yourself with the safety and risk management plan. - Plan and prepare simulations for non-participant activities as required. - Ensure all relevant parties are briefed, delivering pre-exercise briefings if needed. During Exercise - Oversee and manage the timing and execution of the exercise, adjusting as necessary. - Monitor exercise activities to ensure alignment with objectives, adjusting flow as needed. - Actively manage site safety, responding to incidents according to the risk plan. - Simulate activities not performed by participants as required. - Facilitate participant engagement to meet exercise and agency objectives. After Exercise - Participate in debrief sessions, providing feedback on exercise flow and participant engagement. - Contribute observations and insights to the Exercise Evaluation Report. - Complete and submit safety and incident reports for any incidents during the exercise. - Assist in facilitating and leading debriefs as needed. [Insert additional items as required] |
| Exercise Planning Coordinator | Before Exercise - Develop and finalise the detailed exercise plan. - Confirm roles, responsibilities, and appointments within the EXCON structure. - Finalise all required documents (evaluation plans, injects, scenarios). - Complete the scenario and injects, ensuring all elements are fully developed and aligned with objectives. - Distribute essential documents (e.g. exercise plans, participant handbooks, role assignments) to all participants and controllers in advance. - Coordinate pre-exercise briefings and distribute exercise materials. - Establish and confirm a clear communication plan among participants, EXCON, and evaluators. - Conduct a risk assessment and prepare necessary documentation. During Exercise - Coordinate with the Exercise Controller on inject timings and scenario adjustments as needed. After Exercise - Participate in debrief and evaluation processes. [Insert additional items as required] |
| Exercise Facilitator | Before Exercise - Review the scenario, objectives, and prompts to guide participant discussions. - Review the exercise presentation and suggest any necessary changes or updates. During Exercise - Lead discussions and guide participants through each scenario phase. - Pose questions and prompts to encourage engagement and critical thinking. - Facilitate the delivery of the desktop-based functional components of the exercise. - Keep discussions on track, within scope, and aligned with the exercise timeframe. - Provide clarifications on scenarios and objectives as needed. - Coordinate with the Exercise Controller on any necessary adjustments. After Exercise - Contribute observations and insights to debrief and evaluation processes. [Insert additional items as required] |
| Exercise Evaluation Coordinator | Before Exercise - Assign evaluators to specific exercise components, ensuring full coverage. - Brief and train evaluators on observation techniques and assessment criteria. - Distribute evaluation tools, including observation templates and data collection methods. - Conduct a pre-exercise calibration meeting to review objectives, standards, and scoring criteria. - Prepare feedback mechanisms (e.g. feedback forms, debrief sessions) for gathering insights. - Identify key observation points at the venue and station evaluators strategically. During Exercise - Support and coordinate evaluators, providing resources and assistance as needed. - Oversee observation collection to ensure validity and consistency with evaluation standards. After Exercise - Ensure after-action reviews (AARs) and debriefs are conducted, leading them as required. - Collate and analyse evaluator reports to identify key findings and improvement areas. - Draft the final exercise report, consolidating observations, feedback, and recommendations. [Insert additional items as required] |
| Exercise Evaluators | Before Exercise - Review exercise objectives, evaluation criteria, and assigned focus areas. - Familiarise yourself with observation tools and data collection methods. During Exercise - Observe participant actions and interactions according to assigned objectives. - Record observations accurately, focusing on outcomes relevant to exercise performance measures. - Coordinate with the Evaluation Coordinator for any needed clarification or guidance. After Exercise - Conduct debriefs as required. - Submit completed observation notes and any supporting documentation. - Participate in debrief sessions, sharing insights and feedback on observations. [Insert additional items as required] |
| Logistics Coordinator | Before Exercise - Book the venue, ensuring it meets all setup requirements. - Arrange catering based on participant needs and confirm service details. - Send invites and agendas to all participants with event details and expectations. - Confirm all technical requirements (audio-visual aids, communication devices). - Prepare props, special equipment and documents needed for the exercise. - Visit the venue to confirm setup, ensuring equipment (e.g. projectors, seating, staging areas) is in place. - Arrange clear signage to direct participants, observers, and evaluators to appropriate areas. - Arrange inventory supplies, such as name badges, safety equipment, notepads, and pens. - Confirm transportation and parking arrangements, providing relevant information to participants. During Exercise - Open and prepare the venue, ensuring all areas are ready for use. - Confirm catering has arrived, is laid out, and is maintained throughout the event. - Address any logistical needs as they arise to support the smooth flow of activities. After Exercise - Participate in debrief sessions, providing insights on logistics and venue setup. - Contribute feedback and observations to the evaluation report. [Insert additional items as required] |
| Activation Cell | Before Exercise - Review the Master Schedule of Events (MSE) and timeline for injects. - Familiarise yourself with the scenario details and injects. - Prepare materials and tools for delivering injects (e.g., scripts, email templates, props). - Conduct a dry run of the scenario to ensure timing and flow are practical. - Coordinate with the Exercise Controller to confirm inject delivery methods. During Exercise - Monitor the progress of the exercise and ensure injects are delivered on schedule. - Adapt injects in real time if needed to align with exercise objectives. - Track participant actions and decisions in response to injects. - Communicate inject delivery status and exercise flow updates to the Exercise Controller. After Exercise - Compile notes on participant responses to injects for debriefing purposes. - Participate in the post-exercise debrief to provide insights into scenario flow and inject effectiveness. [Insert additional items as required] |
| Observer Coordinator | Before Exercise - Develop and distribute observer joining instructions, including the exercise agenda and objectives. - Confirm a designated viewing area that does not interfere with exercise activities. - Coordinate with logistics to ensure observer needs (e.g., seating, refreshments) are met. During Exercise - Escort observers to the designated viewing area and provide a scenario briefing. - Ensure observers do not disrupt exercise activities or interact with participants. - Address observer questions without interfering with exercise flow. After Exercise - Collect feedback from observers about their experience. - Provide a summary of observer comments during the post-exercise debrief. [Insert additional items as required] |
| Safety Officer | Before Exercise - Review the safety and risk management plan for the exercise. - Familiarise yourself with the exercise layout, activities, and any identified risks. - Conduct a safety briefing for all participants and EXCON team members. - Ensure the availability of safety equipment (e.g., first aid kits, emergency exits). During Exercise - Monitor all exercise activities to ensure compliance with safety protocols. - Immediately intervene and report any safety breaches or incidents to the Exercise Controller. - Document safety concerns or incidents in real time. After Exercise - Participate in debrief sessions to provide a summary of safety observations. - Submit incident reports and recommendations to the Exercise Controller. [Insert additional items as required] |